## Slide 1: Engineering management
PROJECT management

## Slide 2: Project management
Build A
A Done
Build B
B Done
Build C
C Done
Build D
Ship
JAN
FEB
MAR
APR
MAY
JUN
On time!
Projects
Projects are unique, one-time endeavor designed to accomplish a set of objectives in a limited time frame.
Examples of projects include constructing a shopping complex, merging two companies, putting on a play, and designing and running a political campaign.
Examples of projects within business organizations include designing new products or services, designing advertising campaigns, designing information systems, reengineering a process, designing databases, software development, and designing web pages.

## Slide 3: Characteristics of a project
It will have fixed/pre-defined objective(s)
It has limited timeframe within which it should be completed
It has limited budget or resources to accomplish the objectives
Uniqueness: Each project will be unique. Even constructing same building in two different location will have uniqueness in terms of location.
Difference with operations
Operations is continuous process with repetitive tasks, whereas project has a fixed timeframe
Developing a new product is a project, whereas manufacturing the product to supply into market is operations
Operations management focuses of achieving resource efficiency, whereas project management focuses on completing the project with allocated time and budget

## Slide 4: PROJECT LIFE CYCLE
The size, length, and scope of projects vary widely according to the nature and purpose of the project.
Nevertheless, all projects have something in common:
They go through a life cycle, which typically consists of five phases.

## Slide 5: PROJECT LIFE CYCLE
Initiating - This begins the process by outlining the expected costs, benefits, and risks associated with a project.
  It includes defining the major project goals and choosing a project manager.
Planning - This phase provides details on deliverables, the scope of the project, the budget, schedule and milestones, performance objectives, resources needed, a quality plan, and a plan for handling risks.
  The accompanying documents generated in the planning phase will be used in the executing and monitoring phases to guide activities and monitor progress. Members of the project team are chosen.

## Slide 6: PROJECT LIFE CYCLE
Executing - In this phase, the actual work of the project is carried out.
  The project is managed as activities are completed, resources are consumed, and milestones are reached.
  Management involves what the Project Management Institute refers to as the nine management areas: project integration, scope, human resources, communications, time, risk, quality, cost, and procurement.

## Slide 7: PROJECT LIFE CYCLE
Monitoring and Controlling - This phase occurs at the same time as project execution.
  It involves comparing actual progress with planned progress and undertakes corrective action if needed, as well as monitoring any corrective action to make sure it achieves the desired effect.
Closing - This phase ends the project.
  It involves handing off the project deliverables (assuming the project hasn’t been canceled), obtaining customer acceptance, documenting lessons learned and releasing resources.

## Slide 8: Key Decisions in Project Management
Much of the success of projects depends on key managerial decisions over a sequence of steps:
   Deciding which projects to implement.
   Selecting the project manager.
   Selecting the project team.
   Planning and designing the project.
   Managing and controlling project resources.
   Deciding if and when a project should be terminated.

## Slide 9: The Project Manager
The project manager bears the ultimate responsibility for the success or failure of the project.
He or she must be capable of working through others to accomplish the objectives of the project. The project manager is responsible for effectively managing each of the following:
1. The work, so that all of the necessary activities are accomplished in the desired sequence, and performance goals are met.
2. The human resources, so that those working on the project have direction and motivation.
3. Communications, so that everybody has the information needed to do the work.

## Slide 10: The Project Manager
4. Quality, so that performance objectives are realized.
5. Time, so that the project is completed on schedule.
6. Costs, so that the project is completed within budget.
7. Scope, so the project stays within the prescribed scope, and “scope creep” doesn’t occur without commensurate changes to the schedule (if needed) and the budget.

## Slide 11: Project management tools
Project Management Tools:
 Work Breakdown Structure
 Gantt Charts
 PERT and CPM

## Slide 12: Project management tools
 Work Breakdown Structure
Work breakdown structure (WBS) A hierarchical listing of what must be done during a project.
This methodology establishes a logical framework for identifying the required activities for the project.
The first step in developing the work breakdown structure is to identify the major elements of the project. These are the Level 2 boxes.

## Slide 13: Project management tools
 Work Breakdown Structure
The next step is to identify the major supporting activities for each of the major elements - the Level 3 boxes.
Then, each major supporting activity is broken down into a list of the activities that will be needed to accomplish it - the Level 4 boxes.
For purposes of illustration, only a portion of the Level 4 boxes are shown.)
Usually there are many activities in the Level 4 lists.
Large projects involve additional levels, but the figure gives you some idea of the concept of the work breakdown structure.

## Slide 14: Project management tools
 Work Breakdown Structure

## Slide 15: Project management tools
 Gantt Chart
The Gantt chart is a popular visual tool for planning and scheduling simple projects. It enables a manager to initially schedule project activities and then to monitor progress over time by comparing planned progress to actual progress.
The figure illustrates a Gantt chart for a bank’s plan to establish a new direct marketing department.
To prepare the chart, the vice president in charge of the project had to first identify the major activities that would be required.
Next, time estimates for each activity were made, and the sequence of activities was determined.

## Slide 16: Project management tools
 Gantt Chart
Once completed, the chart indicated which activities were to occur, their planned duration, and when they were to occur.
Then, as the project progressed, the manager was able to see which activities were on schedule and which were behind schedule.

## Slide 17: Project management tools
 Gantt Chart

## Slide 18: Project management tools
 PERT and CPM
PERT (Program Evaluation and Review Technique) and CPM (Critical Path Method) are two of the most widely used techniques for planning and coordinating large-scale projects.
By using PERT or CPM, managers are able to obtain:
 A graphical display of project activities
 An estimate of how long the project will take
 An indication of which activities are the most critical to timely project completion
 An indication of how long any activity can be delayed without delaying the project

## Slide 19: Project management tools
Critical Path Analysis
  - Also called critical path method - is a network diagramming technique used to predict total project duration.
- A critical path is the series of activities that determine the earliest time by which the project can be completed.
- The longest path or the path containing the critical tasks is what is driving the completion date for the project.

## Slide 20: Project management tools
Critical Path Analysis
The Network Diagram
One of the main features of PERT and related techniques is their use of a network (or precedence) diagram to depict major project activities and their sequential relationships.
There are two slightly different conventions for constructing these network diagrams.
Under one convention, the arrows designate activities; under the other convention, the nodes designate activities.

## Slide 21: Project management tools
Critical Path Analysis
The Network Diagram
These conventions are referred to as:
Activity-on-Arrow (AOA) and Activity-on-Node (AON)

## Slide 22: Project management tools
Critical Path Analysis
The Network Diagram
Activity
A specific task or set of tasks that are required by the project, use up resources, and take time to complete.
Event
The result of completing one or more activities. An identifiable end state that occurs at a particular time. Events use no resources.

## Slide 23: Project management tools
Critical Path Analysis
The Network Diagram
Network
The arrangement of all activities (and, in some cases, events) in a project arrayed in their logical sequence and represented by arcs and nodes.
This arrangement (network) defines the project and the activity precedence relationships.
Networks are usually drawn starting on the left and proceeding to the right.
Arrowheads placed on the arcs are used to indicate the direction of flow - that is, to show the proper precedences.

## Slide 24: Project management tools
Critical Path Analysis
The Network Diagram
Network (Contd.)
Before an event can be realized—that is, achieved—all activities that immediately precede it must be completed.
These are called its predecessors.
Thus, an event represents an instant in time when each and every predecessor activity has been finished.

## Slide 25: Project management tools
Critical Path Analysis
The Network Diagram
Path
The series of connected activities (or intermediate events) between any two events in a network.
Critical Activities, events, or paths that, if delayed, will delay the completion of the project.
A project’s critical path is understood to mean that sequence of critical activities (and critical events) that connects the project’s start event to its finish event and which cannot be delayed without delaying the project.

## Slide 26: Project management tools
Critical Path Analysis
The Network Diagram
To transform a project plan into a network, one must know what activities comprise the project and, for each activity, what its predecessors (or successors) are.
An activity can be in any of these conditions:
it may have a successor(s) but no predecessor(s);
it may have a predecessor(s) but no successor(s); and
it may have both predecessor(s) and successor(s).

## Slide 27: Project management tools
Critical Path Analysis
The Network Diagram
The first of these is an activity that starts a network.
The second ends a network.
The third is in the middle.
Figure 8.1 shows each of the three types of activities.

## Slide 28: Project management tools
Critical Path Analysis
The Network Diagram
Activities are represented here by rectangles (one form of what in a network are called “nodes”) with arrows to show the precedence relationships.
When there are multiple activities with no predecessors, it is usual to show them all emanating from a single node called “START”, as in Figure 8.2.
Similarly, when multiple activities have no successors, it is usual to show them connected to a node called “END”.

## Slide 29: Project management tools
Critical Path Analysis
The Network Diagram

## Slide 30: Project management tools
Critical Path Analysis
The Network Diagram
In the preceding examples, rectangles (nodes) represented the activities; hence, it was called an activity-on-node (AON) network.
Another format for drawing networks is activity-on-arrow (AOA), as shown in Figure 8.3.
Here, the activities are shown on the arrows, and the (circular) nodes represent events.
If the project begins with multiple activities, they can all be drawn emanating from the initial node, and multiple activities can terminate in a single node at the end of the project.

## Slide 31: Project management tools
Critical Path Analysis
The Network Diagram

## Slide 32: Project management tools
Critical Path Analysis
The Network Diagram

## Slide 33: Project management tools
Critical Path Analysis
The Network Diagram

## Slide 34: Project management tools
Critical Path Analysis
The Network Diagram

## Slide 35: Project management tools
Critical Path Analysis
The Network Diagram
Paths that are shorter than the critical path can experience some delays and still not affect the overall project completion time as long as the ultimate path time does not exceed the length of the critical path.
The allowable slippage for any path is called slack, and it reflects the difference between the length of a given path and the length of the critical path.
The critical path, then, has zero slack time.

## Slide 36: Project management tools
Critical Path Analysis

## Slide 37: Project management tools
 Draw Precedence diagram and find critical path and expected project duration

## Slide 38: Project management tools
ACITIVITY | Duration | Immediate Predecessor
A | 1 Day | n/a
B | 2 Days | n/a
C | 3 Days | n/a
D | 4 Days | A
E | 5 Days | B
F | 4 Days | B
G | 6 Days | C
H | 6 Days | D, E
I | 2 Days | G
J | 3 Days | H, F, I

## Slide 39: Project management tools
Critical Path Analysis
Path 1 : A – D – H - J
Path 2 : B – E – H - J
Path 3 : B – F – J
Path 4 : C – G – I - J
Start
A,1
B,2
C,3
D,4
E,5
F,4
G,6
H,6
I,2
J,3
End

## Slide 40: Project management tools
Critical Path Analysis
Path 1 : A – D – H - J
Path 2 : B – E – H - J
Path 3 : B – F – J
Path 4 : C – G – I - J
Start
A,1
B,2
C,3
D,4
E,5
F,4
G,6
H,6
I,2
J,3
End
Length 1 : 1+4+6+3 = 14 days
Length 2 : 2+5+6+3 = 16 days
Length 3 : 2+4+3 = 9 days
Length 4 : 3+6+2+3 = 14 days

## Slide 41: Gantt chart
 | 1 | 2 | 3 | 4 |  |  | 7 | 8 | 9 |  |  |  |  |  |  | 16
A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
J |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 42: Project management tools
Critical Path Analysis
Because the critical path is the longest path through the network diagram,
therefore Path 2: B-E-H-J, is the critical path for Project X
Start
A,1
B,2
C,3
D,4
E,5
F,4
G,6
H,6
I,2
J,3
End

## Slide 43: Project management tools
Critical Path Analysis
Identifying the Critical Path; Computing Project Duration and Slack Times for Deterministic Times Given the additional information on the bank network of Figure 17.4 shown in Figure 17.5, determine the following.
The length of each path
The critical path
The expected length of the project
The amount of slack time for each path

## Slide 44: Project management tools
Critical Path Analysis

## Slide 45: Project management tools
Critical Path Analysis

## Slide 46: Project management tools
Critical Path Analysis
Activity Name
Duration
ES
EF
LS
LF
Activity Name
Duration
ES
EF
LS
LF
Notes :
ES : Earliest Start = 16th april
EF : Earliest Finish = 17th april
Notes :
LS : Latest Start = 29th april
LF : Latest Finish = 30th april

## Slide 47: Project management tools
Critical Path Analysis
D, 5
4
E, 3
9
31
36
G, 2
10
12
34
36
?
?
Forward Calculation

## Slide 48: Project management tools
Critical Path Analysis
D, 5
4
E, 3
9
31
36
G, 2
10
12
34
36
12
15
Have to take the Higher EF for the Immediate Successor (E)
Forward Calculation

## Slide 49: Project management tools
Critical Path Analysis
H, 16
10
I, 4
26
?
?
J, 8
26
34
26
34
26
30
36
40
Backward Calculation

## Slide 50: Project management tools
Critical Path Analysis
H, 16
10
I, 4
26
10
26
J, 8
26
34
26
34
26
30
36
40
Backward Calculation
Have to take the Lowest LS for the Immediate Predecessor (H)

## Slide 51: Project management tools
Critical Path Analysis
Sample Problem #1
Activity | Immediate Predecessor(s) | Duration (Weeks) |  | Activity | Immediate Predecessor(s) | Duration (Weeks)
N |  | 5 |  | G | B | 2
A | N | 4 |  | H | B | 16
B | N | 10 |  | I | H | 4
C | N | 7 |  | J | H | 8
D | A | 5 |  | K | I, J, L | 5
E | D, G | 3 |  | L | C | 9
F | E | 6 |  | M | J, L | 10

## Slide 52: Project management tools
Critical Path Analysis
Sample Problem #1
a) Draw the network diagram and find the critical path and project completion time.
b) Calculate float/ slack of the all activities.
c) Can activity I be delayed without delaying the project completion time? If so, how many weeks? How much dollar can be saved by keeping the project completion time unchanged, if $2500 can be saved for each delayed week of activity I?
d) What is the impact on the project if activity F needs a delayed time 2 weeks and extra time 5 weeks?
e) The PM wants to delay the duration of the activity M from 10 weeks to 16 weeks. What is the impact on the project completion time?

## Slide 53: Project management tools
Critical Path Analysis
Start
N,5
A,4
B,10
C,7
D,5
G,2
E,3
H,16
I,4
J,8
L,9
K,5
M,10
F,6
End
0
0
0
5
5
9
9
14
17
20
5
5
15
12
15
17
20
26
15
31
12
31
35
39
31
39
44
39
49
49
49
49
49
49
43
43
40
49
39
49
44
39
30
39
31
44
40
31
15
40
38
40
35
35
31
5
15
30
23
0
5
0
0
EF = ES + Duration (Forward)
LS = LF – Duration (Backward)
Module (Applied when path crossed)
Sample Problem #1
21

## Slide 54: Project management tools
Critical Path Analysis
Start
N,5
A,4
B,10
C,7
D,5
G,2
E,3
H,16
I,4
J,8
L,9
K,5
M,11
F,6
End
0
0
0
5
5
9
9
14
17
20
5
5
15
12
15
17
20
26
15
31
12
31
35
39
31
39
44
39
50
50
50
40
39
30
31
40
31
15
40
38
40
35
35
31
5
15
30
23
0
5
0
0
EF = ES + Duration (Forward)
LS = LF – Duration (Backward)
Module (Applied when path crossed)
Sample Problem #1
21
49
49
49
49
49
43
44
39
43
44
39

## Slide 55: Project management tools
Critical Path Analysis
Project Completion Time = 49 weeks
Path 1 = N – A – D – E – F = 23 weeks
Path 2 = N – B – G – E – F = 26 weeks
Path 3 = N – B – H – I – K = 40 weeks
Path 4 = N – B – H – J – K = 44 weeks
Path 5 = N – B – H – J – M = 49 weeks (maximum)
Path 6 = N – C – L – K = 26 weeks
Path 7 = N – C – L – M = 31 weeks
Critical Path = Path 5 = N+B+H+J+M = 49 weeks
Critical Activities = B, H, J, M, and N (Where the Slack is 0)
Non-Critical Activities = A, C, D, E, F, G, I, K, and L
So, project will require minimum 49 weeks to complete
Sample Problem # 1

## Slide 56: Project management tools
Critical Path Analysis
Project Completion Time = 49 weeks
Slack = LS – ES ||| LF - EF
Slack A = 31- 5 = 26
Slack B = 5 - 5 = 0
Slack C = 23-5 = 18
Slack D = 35-9 = 26
Slack E = 40-17 = 23
Slack F = 43-20 = 23
Slack G = 38-15 = 23
Slack H = 15 – 15 = 0
Slack I = 40 – 31 = 9
Slack J = 31 – 31 = 0
Slack K = 44 – 39 = 5
Slack L = 30 – 12 = 18
Slack M = 39 – 39 = 0
Slack N = 0 – 0 = 0
Sample Problem #1

## Slide 57: Project management tools
Critical Path Analysis
Sample Problem #1
c) Can activity I be delayed without delaying the project completion time?
If so, how many weeks?
How much dollar can be saved by keeping the project completion time unchanged, if $2500 can be saved for each delayed week of activity I?
Yes, the Activity “I” can be delayed as it is a non-critical activity. It can be delayed upto the value of slack that is for 9 weeks.
Activity I has a slack of 9 weeks, so, $2500*9= $22,500/- can be saved by keeping the project completion time unchanged.

## Slide 58: Project management tools
Critical Path Analysis
Sample Problem #1
d) What is the impact on the project if activity F needs a delayed time 2 weeks and extra time 5 weeks?
According to the question, activity F needs to delay by 2+5= 7 weeks, it is possible by keeping the project completion time unchanged as F is a non-critical activity with a slack of 23 weeks.

## Slide 59: Project management tools
Critical Path Analysis
Sample Problem #1
e) The PM wants to delay the duration of the activity M from 10 weeks to 16 weeks. What is the impact on the project completion time?
According to the question, if the Project Manager wants to delay the
duration of the activity M from 10 weeks to 16 weeks, then it will delay the entire duration of the project.
As activity M, falls under critical activity of the project, therefore the Slack of activity M is 0.
It will eventually increase the project duration to more 6 days (a total of 49+6 = 55 days) to complete the project in this situation.

## Slide 60: Project management tools
Critical Path Analysis
Sample Problem # 2
Activity | Immediate Predecessor(s) | Duration (Weeks) |  | Activity | Immediate Predecessor(s) | Duration (Weeks)
A |  | 4 |  | F | B | 6
B |  | 10 |  | G | C | 2
C |  | 7 |  | H | F | 8
D | A | 5 |  | I | F, G | 11
E | B | 3 |  | J | D, E | 8

## Slide 61: Project management tools
Critical Path Analysis
Sample Problem # 2
Draw a network diagram and find the critical path and project completion time.
Calculate float/ slack of the all activities.
If $1000 can be saved for each delayed weeks of activity H, then how much dollar can be saved keeping the project completion time unchanged?
Activity G needs a delayed time of two weeks and an extra time of five weeks. Is it possible by keeping the project completion time unchanged? Explain.
The PM wants to shorten the duration of the activity I from 11 weeks to 9 weeks. What is the impact of this change on project completion time

## Slide 62
END OF THE CHAPTER